## i need you to reformat it as fo
User Story | Description | Acceptance Criteria | Priority | Estimated Effort (Story Points) | Dependencies | Status
User Registration API (Backend) | As a new user, I want to register for the platform by providing my email, password, and profile details so that I can create an account. | API allows users to submit email, password, and profile information. Validation on email format and password strength. User account is created successfully in the database. JWT token is generated and sent upon successful registration. Errors for invalid input should return appropriate error messages. | High | 5 | Database Design | To Do
Login API (Backend) | As a registered user, I want to log in to the platform so that I can access my account securely. | API allows registered users to log in using email and password. JWT token is issued upon successful login. Invalid login attempts should return an error. Login details should be stored securely and follow security best practices. | High | 5 | User Registration API | To Do
User Profile UI (Web) | As a logged-in user, I want to view and edit my profile information so that I can update my personal details. | Web UI should display the user's profile information. Form validation for all input fields (e.g., email, phone number). Users should be able to update their information. Changes should be reflected in the database via API. | Medium | 3 | User Registration API | To Do
User Profile UI (Mobile) | As a logged-in mobile user, I want to view and edit my profile on the app so that I can update my information. | Mobile UI should display user profile info. Mobile layout should adapt to different screen sizes. Profile update should use the same API as the web. Smooth navigation and responsiveness on mobile devices. | Medium | 3 | User Registration API, Mobile Design | To Do
Product Catalog API (Backend) | As a user, I want to browse the product catalog so that I can view available products. | API returns a list of products with details (name, description, price, image). API supports filtering and sorting by category, price, etc. API handles pagination for large catalogs. | High | 5 | Database Design, Product Data | To Do
Product Listing UI (Web) | As a web user, I want to see a list of products so that I can browse and filter available items. | UI displays product data (name, price, description, image) retrieved from API. Users can filter products by category, price, etc. The UI is responsive and adjusts to different screen sizes. | High | 3 | Product Catalog API | To Do
Product Listing UI (Mobile) | As a mobile user, I want to view and filter the product catalog so that I can browse available products on my phone. | Mobile UI displays the product list retrieved from API. Users can filter products by category or price. Layout adapts to different mobile screen sizes. | High | 3 | Product Catalog API | To Do
Add to Cart API (Backend) | As a user, I want to add items to my shopping cart so that I can purchase them later. | API adds selected product to the user's cart. The cart persists across sessions (using sessions or cookies). Cart total price is calculated automatically. Errors for invalid product IDs or stock unavailability should be handled gracefully. | High | 5 | Product Catalog API | To Do
Shopping Cart UI (Web) | As a web user, I want to view and update my shopping cart so that I can proceed to checkout. | UI displays all items in the cart with quantity and price. Users can add or remove items from the cart. The total price is updated in real-time. Cart changes are persisted using the API. | Medium | 4 | Add to Cart API | To Do
Shopping Cart UI (Mobile) | As a mobile user, I want to view my shopping cart so that I can proceed to checkout on my phone. | Mobile UI displays the cart items retrieved from API. Users can add/remove items from the cart. The UI adapts to different mobile screen sizes. | Medium | 4 | Add to Cart API | To Do
Payment Processing API (Backend) | As a user, I want to pay for my order securely so that my transaction is completed. | API integrates with payment gateway (e.g., Stripe/PayPal). Payment status is validated and returned. Errors in payment processing are handled gracefully. The system should follow PCI compliance guidelines. | High | 5 | Order Management | To Do
Payment UI (Web) | As a web user, I want to securely enter my payment details so that I can complete my purchase. | UI collects payment information. Data is securely transmitted to the backend. User is notified of payment success or failure. The UI follows security best practices. | High | 3 | Payment Processing API | To Do
Payment UI (Mobile) | As a mobile user, I want to securely enter payment details so that I can complete my purchase on the go. | Mobile UI collects payment info. Data is transmitted securely to the backend. The user receives clear feedback on payment status. | High | 3 | Payment Processing API | To Do
Comprehensive Testing | As a developer, I want to ensure that the entire system works as expected so that users have a seamless experience. | Functional testing for all modules (user, product, cart, order). Integration testing between backend and frontend. Load testing for performance. Security testing for vulnerabilities. | High | 10 |  | To Do