## Sheet1
Sprint | Duration | Milestone | Start Date | End Date | Backend Development Activities | UI Development Activities | Mobile Development Activities | Deliverables | Responsible | Notes
1. Project Initiation | 1 Week | Project Kickoff | 2024-09-22 | 2024-09-28 | - Define project goals and objectives - Identify stakeholders | - Define UI requirements - Initial wireframe sketches | - Define mobile requirements - Initial wireframe sketches | - Project Charter - Stakeholder List - Initial Backlog | Project Manager | Conduct kickoff meeting with all stakeholders.
2. Sprint 0: Database Design | 2 Weeks | Database Design Complete | 2024-09-29 | 2024-10-12 | - Analyze requirements - Define database schema - Design database architecture | - Review database design for UI impact | - Review database design for mobile impact | - ER Diagrams - Initial Database Schema | DB Developer | Review design with the team.
[5 empty] | - Implement and test the schema - Document design and setup instructions | - Prepare UI mockups based on schema | - Prepare mobile mockups based on schema | - Database Setup Documentation | DB Developer | Include basic data population.
3. Sprint 1 | 2 Weeks | User Management Complete | 2024-10-13 | 2024-10-26 | - Develop API for user registration and login - Implement authentication | - Design UI for user registration and login - Create wireframes and prototypes | - Design mobile UI for user registration and login - Create wireframes and prototypes | - User Management API - UI Wireframes | Backend Developer UI/UX Designer Mobile Developer | Conduct integration testing between UI and API.
[5 empty] | - Integrate with UI - Perform testing and document API endpoints | - Implement UI components - Integrate with backend API | - Implement mobile UI components - Integrate with backend API | - Functional User Management UI - Functional Mobile UI | Frontend Developer Mobile Developer | Ensure mobile responsiveness.
4. Sprint 2 | 2 Weeks | Product Management Complete | 2024-10-27 | 2024-11-09 | - Develop API for product management - Implement search and filtering | - Design UI for product listing and search - Create wireframes and prototypes | - Design mobile UI for product listing and search - Create wireframes and prototypes | - Product Management API - UI Wireframes | Backend Developer UI/UX Designer Mobile Developer | Conduct user testing on prototypes.
[5 empty] | - Integrate with UI - Perform testing and document API endpoints | - Implement UI components - Integrate with backend API | - Implement mobile UI components - Integrate with backend API | - Functional Product Management UI - Functional Mobile UI | Frontend Developer Mobile Developer | Optimize for performance.
5. Sprint 3 | 2 Weeks | Shopping Cart Complete | 2024-11-10 | 2024-11-23 | - Develop API for shopping cart - Implement persistence and calculations | - Design UI for shopping cart - Create wireframes and prototypes | - Design mobile UI for shopping cart - Create wireframes and prototypes | - Shopping Cart API - UI Wireframes | Backend Developer UI/UX Designer Mobile Developer | Focus on user-friendly interactions.
[5 empty] | - Integrate with UI - Perform testing and document API endpoints | - Implement UI components - Integrate with backend API | - Implement mobile UI components - Integrate with backend API | - Functional Shopping Cart UI - Functional Mobile UI | Frontend Developer Mobile Developer | Validate cart functionality on mobile devices.
6. Sprint 4 | 2 Weeks | Order Management Complete | 2024-11-24 | 2024-12-07 | - Develop API for order processing - Implement order status tracking | - Design UI for order processing - Create wireframes and prototypes | - Design mobile UI for order processing - Create wireframes and prototypes | - Order Management API - UI Wireframes | Backend Developer UI/UX Designer Mobile Developer | Ensure clarity in order details.
[5 empty] | - Integrate with UI - Perform testing and document API endpoints | - Implement UI components - Integrate with backend API | - Implement mobile UI components - Integrate with backend API | - Functional Order Management UI - Functional Mobile UI | Frontend Developer Mobile Developer | Test for responsiveness and speed.
7. Sprint 5 | 2 Weeks | Payment Integration Complete | 2024-12-08 | 2024-12-21 | - Integrate with payment gateway - Implement payment processing | - Design UI for payment processing - Create wireframes and prototypes | - Design mobile UI for payment processing - Create wireframes and prototypes | - Payment Processing API - UI Wireframes | Backend Developer UI/UX Designer Mobile Developer | Ensure security in payment forms.
[5 empty] | - Integrate with UI - Perform testing and document API endpoints | - Implement UI components - Integrate with backend API | - Implement mobile UI components - Integrate with backend API | - Functional Payment Processing UI - Functional Mobile UI | Frontend Developer Mobile Developer | Conduct usability tests for payment flows.
8. Sprint 6 | 2 Weeks | Admin Dashboard Complete | 2024-12-22 | 2025-01-04 | - Develop API for admin functions - Implement reporting features | - Design UI for admin dashboard - Create wireframes and prototypes | - Design mobile UI for admin functions - Create wireframes and prototypes | - Admin API - UI Wireframes | Backend Developer UI/UX Designer Mobile Developer | Include data visualization components.
[5 empty] | - Integrate with UI - Perform testing and document API endpoints | - Implement UI components - Integrate with backend API | - Implement mobile UI components - Integrate with backend API | - Functional Admin Dashboard UI - Functional Mobile UI | Frontend Developer Mobile Developer | Validate role-based access on mobile.

## Sheet2
Phase | Duration | Milestone | Week | Tasks
1. Project Initiation | 1 Week | Project Kickoff | Week 1 | - Define project goals and objectives - Identify stakeholders (list all stakeholders and their roles) - Establish project team and roles (assign roles such as Product Owner, Scrum Master, Developers, and Designers) - Set up initial backlog with user stories and requirements (create user stories with acceptance criteria)
2. Sprint 0: Database Design | 2 Weeks | Database Design Complete | Week 1 | - Analyze requirements and define the database schema (review user stories and identify data entities) - Design database architecture and relationships (create ER diagrams to illustrate relationships) - Create initial database schema (define tables and relationships in SQL) - UI Development: Create wireframes for user management and product management UI, including mobile application layouts (use Figma or Sketch, create high-fidelity wireframes focusing on layout, navigation, and interaction).
|  |  | Week 2 | - Implement and test the database schema (create tables, indexes, and constraints in the database) - Set up initial data and perform basic database operations (insert sample data and validate CRUD operations) - Document database design and setup instructions (create a detailed document for developers) - UI Development: Refine wireframes based on stakeholder feedback and prepare for the next sprints (conduct review sessions, adjust based on user feedback).
3. Sprint 1: Backend User Management | 2 Weeks | User Management Backend Complete | Week 1 | - Develop backend API for user registration, login, and profile management (use RESTful practices to define endpoints) - Implement authentication (JWT) and authorization (roles) - Design database tables for user data (user table, profile table, etc.).
|  |  | Week 2 | - Integrate backend user management with UI (develop endpoints for registration and login) - Perform unit testing and initial integration testing (use tools like Postman or Swagger for testing) - Document API endpoints and usage (create API documentation using Swagger or Postman) - UI Development: Implement user registration and login UI components for both web and mobile views (use React or Angular for web, React Native for mobile; ensure forms include validations, error messages, and responsive design).
4. Sprint 2: Backend Product Management | 2 Weeks | Product Management Backend Complete | Week 1 | - Develop backend API for product catalog management (define endpoints for CRUD operations) - Implement product search and filtering capabilities (use query parameters for search functionality) - Design database tables for product data (product table, category table, etc.).
|  |  | Week 2 | - Integrate backend product management with UI (connect product API to frontend components) - Perform unit testing and integration testing (ensure all product-related functionalities work) - Document API endpoints and usage (update API documentation) - UI Development: Design and implement product listing and search UI for both web and mobile interfaces (create responsive layouts using CSS frameworks like Bootstrap or Tailwind; ensure smooth filtering and search experiences).
5. Sprint 3: Backend Shopping Cart | 2 Weeks | Shopping Cart Backend Complete | Week 1 | - Develop backend API for shopping cart management (define endpoints for adding/removing items) - Implement cart persistence (use sessions or cookies) and calculation logic (total price calculations) - Ensure data validation and error handling (return appropriate error messages).
|  |  | Week 2 | - Integrate backend shopping cart with UI (connect cart API to shopping cart UI components) - Perform unit testing and integration testing (test cart functionalities) - Document API endpoints and usage (update API documentation) - UI Development: Build and refine shopping cart UI components, including mobile views (design cart dropdown or dedicated page, ensure seamless transitions when adding/removing items, and provide clear feedback to users).
6. Sprint 4: Backend Order Management | 2 Weeks | Order Management Backend Complete | Week 1 | - Develop backend API for order processing (define endpoints for checkout, order history) - Implement order status tracking (order statuses such as pending, completed) and management - Ensure data integrity during order placement (validation checks).
|  |  | Week 2 | - Integrate backend order management with UI (connect order API to order UI components) - Perform unit testing and integration testing (ensure order functionalities work) - Document API endpoints and usage (update API documentation) - UI Development: Create order checkout and order history UI components for web and mobile platforms (design a multi-step checkout process, ensure a responsive design that fits various screen sizes).
7. Sprint 5: Backend Payment Integration | 2 Weeks | Payment Integration Backend Complete | Week 1 | - Develop backend integration with payment gateway (e.g., Stripe, PayPal) (set up credentials and test environment) - Implement payment processing and validation (handle payment responses and errors) - Ensure PCI compliance and security measures are in place (data encryption).
|  |  | Week 2 | - Integrate payment backend with UI (connect payment API to payment forms) - Perform unit testing and integration testing (test payment functionalities) - Document API endpoints and usage (update API documentation) - UI Development: Design and implement payment UI components for web and mobile applications (focus on user-friendly forms with clear instructions, implement error handling for payment issues, ensure mobile layout is intuitive).
8. Sprint 6: Backend Administration and Reporting | 2 Weeks | Admin and Reporting Backend Complete | Week 1 | - Develop backend API for administrative functions (define endpoints for user and product management) - Implement reporting features (sales reports, user activity logging) - Ensure proper authentication and access control for admin features (use role-based access).
|  |  | Week 2 | - Integrate backend admin features with UI (connect admin API to dashboard components) - Perform unit testing and integration testing (test admin functionalities) - Document API endpoints and usage (update API documentation) - UI Development: Create admin dashboard and reporting UI components for web and mobile (design dashboards using data visualization libraries like Chart.js or D3.js, ensure mobile compatibility).
9. Sprint 7: Final Testing and Refinements | 2 Weeks | Final Testing Complete | Week 1 | - Conduct comprehensive testing (functional, integration, performance) (develop test cases for each component) - Fix any bugs or issues found during testing (prioritize bugs based on severity) - Ensure all user stories are met (review with stakeholders).
|  |  | Week 2 | - Perform final rounds of testing and QA (focus on end-to-end testing) - Prepare deployment documentation and user manuals (create step-by-step guides) - UI Development: Finalize and polish all UI components based on testing feedback (ensure mobile usability, check for cross-browser compatibility).
10. Deployment and Post-Deployment Support | 1 Week | Go-Live | Week 1 | - Deploy the website and mobile application to production (follow deployment checklist) - Monitor deployment and perform post-deployment testing (check for critical issues) - Provide initial support and address any post-deployment issues (set up support channels).
11. Post-Launch Review and Iteration | 1 Week | Post-Launch Review Complete | Week 1 | - Collect user feedback (surveys, interviews) and review project performance - Address any critical issues or required changes (prioritize changes based on feedback) - Plan for future iterations or enhancements based on feedback (define backlog for future sprints).

## Sheet3
Phase | Duration | Milestone | Week | Dates | Backend Development | UI Development | Mobile Development
1. Project Initiation | 1 Week | Project Kickoff | Week 1 | 22/09/2024 - 28/09/2024 | - Define project goals and objectives - Identify stakeholders and roles - Establish project team - Set up initial backlog with user stories | - Define wireframe expectations - Outline initial UI requirements - Prepare for feedback cycle | - Define mobile UI requirements - Prepare initial user stories
2. Sprint 0: Database Design | 2 Weeks | Database Design Complete | Week 1 | 29/09/2024 - 05/10/2024 | - Analyze requirements and define database schema - Design database architecture (ER diagrams) - Create initial database schema (SQL) | - Design wireframes for user/product management (Figma/Sketch) | - Design wireframes for mobile user/product management UI (Figma)
|  |  | Week 2 | 06/10/2024 - 12/10/2024 | - Implement and test database schema - Validate CRUD operations - Document database design | - Refine wireframes based on feedback | - Refine wireframes based on feedback
3. Sprint 1: Backend User Management | 2 Weeks | User Management Backend Complete | Week 1 | 13/10/2024 - 19/10/2024 | - Develop API for user registration, login, and profile - Implement JWT authentication and authorization - Design user database tables | - Start creating UI for user registration and login components - Implement form validation | - Start developing mobile user registration and login UI components - Implement form validation
|  |  | Week 2 | 20/10/2024 - 26/10/2024 | - Integrate backend with UI - Perform unit and integration testing using tools (Postman, Swagger) | - Complete UI for user registration/login (web) - Ensure responsive design | - Complete mobile user registration/login UI - Perform initial testing on mobile platform
4. Sprint 2: Backend Product Management | 2 Weeks | Product Management Backend Complete | Week 1 | 27/10/2024 - 02/11/2024 | - Develop API for product catalog CRUD - Implement product search and filtering - Design product-related database tables | - Design UI for product listing and search (responsive, using CSS frameworks) | - Design mobile UI for product listing and search
|  |  | Week 2 | 03/11/2024 - 09/11/2024 | - Integrate backend with UI - Perform unit and integration testing | - Implement product listing and search UI (web) - Ensure smooth filtering experience | - Implement mobile product listing and search UI - Ensure responsiveness
5. Sprint 3: Backend Shopping Cart | 2 Weeks | Shopping Cart Backend Complete | Week 1 | 10/11/2024 - 16/11/2024 | - Develop API for shopping cart management - Implement cart persistence and calculation logic - Ensure data validation | - Design shopping cart UI components (cart dropdown or dedicated page) | - Design mobile shopping cart UI
|  |  | Week 2 | 17/11/2024 - 23/11/2024 | - Integrate backend with UI - Perform unit and integration testing | - Build and refine shopping cart UI components - Ensure smooth transitions when adding/removing items | - Implement mobile shopping cart UI - Test for seamless transitions on mobile
6. Sprint 4: Backend Order Management | 2 Weeks | Order Management Backend Complete | Week 1 | 24/11/2024 - 30/11/2024 | - Develop API for order processing - Implement order status tracking and validation checks | - Design UI for order checkout and order history (multi-step checkout) | - Design mobile order checkout and order history UI
|  |  | Week 2 | 01/12/2024 - 07/12/2024 | - Integrate backend with UI - Perform unit and integration testing | - Implement order checkout/order history UI - Ensure responsiveness | - Implement mobile order checkout/order history UI
7. Sprint 5: Backend Payment Integration | 2 Weeks | Payment Integration Backend Complete | Week 1 | 08/12/2024 - 14/12/2024 | - Integrate with payment gateway (Stripe, PayPal) - Implement payment validation - Ensure PCI compliance | - Design payment UI components (web) - Ensure user-friendly forms and clear instructions | - Design mobile payment UI components
|  |  | Week 2 | 15/12/2024 - 21/12/2024 | - Integrate payment backend with UI - Perform unit and integration testing | - Implement payment UI components - Ensure error handling for payment issues | - Implement mobile payment UI components - Test for mobile compatibility
8. Sprint 6: Admin and Reporting | 2 Weeks | Admin and Reporting Backend Complete | Week 1 | 22/12/2024 - 28/12/2024 | - Develop API for admin functions (user/product management) - Implement reporting features (sales, logs) - Ensure access control for admin roles | - Design admin dashboard and reports (Chart.js or D3.js for data visualization) | - Design mobile admin dashboard and reports
|  |  | Week 2 | 29/12/2024 - 04/01/2025 | - Integrate backend with admin UI - Perform unit and integration testing | - Implement admin dashboard UI - Ensure mobile responsiveness | - Implement mobile admin dashboard UI
9. Sprint 7: Final Testing and Refinements | 2 Weeks | Final Testing Complete | Week 1 | 05/01/2025 - 11/01/2025 | - Perform comprehensive testing (functional, integration, performance) - Bug fixing | - Finalize and polish all UI components (web) | - Finalize and polish all mobile UI components
|  |  | Week 2 | 12/01/2025 - 18/01/2025 | - Perform final testing and QA - Prepare deployment documentation/user manuals | - Ensure cross-browser compatibility | - Ensure mobile usability is tested across devices
10. Deployment and Post-Support | 1 Week | Go-Live | Week 1 | 19/01/2025 - 25/01/2025 | - Deploy backend to production environment - Monitor post-deployment testing | - Deploy web UI to production - Monitor UI in production | - Deploy mobile app to app stores - Monitor for any issues
11. Post-Launch Review & Iteration | 1 Week | Post-Launch Review Complete | Week 1 | 26/01/2025 - 01/02/2025 | - Collect user feedback - Plan for future iterations based on feedbac

## Sheet4
Phase | Duration | Milestone | Week | Dates | Backend Tasks | UI (Web) Tasks | Mobile Tasks
1. Project Initiation | 1 Week | Project Kickoff | Week 1 | 22/09/2024 - 28/09/2024 | - Define project goals and objectives - Identify stakeholders and roles - Establish project team - Set up backlog with user stories and acceptance criteria | - Participate in backlog creation to define UI stories and requirements | - Participate in backlog creation to define mobile-specific stories and requirements
2. Sprint 0: Database Design | 2 Weeks | Database Design Complete | Week 1 | 29/09/2024 - 05/10/2024 | - Analyze requirements and define the database schema - Design database architecture (ER diagrams) - Create initial database schema (SQL) | - Create initial wireframes for user and product management (Figma/Sketch) | - Design initial wireframes for mobile UI (React Native) - Consider responsive and adaptive layouts
|  |  | Week 2 | 06/10/2024 - 12/10/2024 | - Implement and test the database schema (CRUD operations) - Insert sample data - Document database design and setup instructions | - Refine wireframes based on stakeholder feedback | - Refine mobile wireframes based on stakeholder feedback
3. Sprint 1: Backend User Management | 2 Weeks | User Management Backend Complete | Week 1 | 13/10/2024 - 19/10/2024 | - Develop API for user registration, login, and profile management (JWT authentication) - Design user database tables (user, profile, roles) | - Design user registration and login UI components (React/Angular) - Ensure forms include validations, error messages, and responsive design | - Design user registration and login UI for mobile (React Native) - Ensure proper validation and error handling
|  |  | Week 2 | 20/10/2024 - 26/10/2024 | - Integrate backend with frontend (REST APIs) - Perform unit and integration testing (Postman/Swagger) - Document API endpoints and usage | - Implement user registration/login UI - Test web forms for validations and security | - Implement mobile user registration/login UI - Ensure seamless navigation and test mobile form validations
4. Sprint 2: Backend Product Management | 2 Weeks | Product Management Backend Complete | Week 1 | 27/10/2024 - 02/11/2024 | - Develop API for product catalog management (CRUD operations) - Implement product search and filtering - Design product-related database tables | - Design product listing, search, and filtering UI (React/Angular) - Focus on responsive layouts using CSS frameworks like Bootstrap or Tailwind | - Design mobile product listing, search, and filtering UI - Ensure smooth filtering and adaptive layout
|  |  | Week 2 | 03/11/2024 - 09/11/2024 | - Integrate backend product APIs with frontend - Perform unit and integration testing - Document product API endpoints | - Implement product listing/search UI - Test for responsiveness and performance | - Implement mobile product listing/search UI - Test for smooth filtering and user experience
5. Sprint 3: Backend Shopping Cart | 2 Weeks | Shopping Cart Backend Complete | Week 1 | 10/11/2024 - 16/11/2024 | - Develop API for shopping cart management (add/remove items) - Implement cart persistence (sessions/cookies) - Implement total price calculations | - Design shopping cart UI components (React/Angular) - Create cart dropdowns or dedicated page layout - Focus on clear user feedback during interactions | - Design shopping cart UI for mobile - Ensure seamless adding/removing items and responsive layout
|  |  | Week 2 | 17/11/2024 - 23/11/2024 | - Integrate backend cart APIs with frontend - Perform unit and integration testing - Document cart API endpoints | - Implement shopping cart UI components - Ensure seamless transitions between cart actions (add/remove items) | - Implement mobile shopping cart UI - Test responsiveness and transitions during cart operations
6. Sprint 4: Backend Order Management | 2 Weeks | Order Management Backend Complete | Week 1 | 24/11/2024 - 30/11/2024 | - Develop API for order processing (checkout, order history) - Implement order status tracking and validation | - Design order checkout and order history UI components (React/Angular) - Create a multi-step checkout process | - Design order checkout and order history UI for mobile - Ensure intuitive flow in mobile checkout
|  |  | Week 2 | 01/12/2024 - 07/12/2024 | - Integrate backend order APIs with frontend - Perform unit and integration testing - Document order API endpoints | - Implement order checkout and order history UI - Ensure proper validations and clear error messages | - Implement mobile order checkout and order history UI - Test for smooth checkout process and responsive layout
7. Sprint 5: Backend Payment Integration | 2 Weeks | Payment Integration Backend Complete | Week 1 | 08/12/2024 - 14/12/2024 | - Develop API integration with payment gateway (Stripe, PayPal) - Implement payment processing and validation (handle responses and errors) - Ensure PCI compliance | - Design payment UI components (React/Angular) - Focus on user-friendly forms with clear instructions | - Design payment UI for mobile - Ensure mobile-friendly forms with proper error handling
|  |  | Week 2 | 15/12/2024 - 21/12/2024 | - Integrate payment backend with frontend (web/mobile) - Perform unit and integration testing (payment processing scenarios) - Document API endpoints | - Implement payment UI components - Test for validation and seamless payment flow | - Implement payment UI components for mobile - Test for responsive design and payment flow on mobile
8. Sprint 6: Admin and Reporting | 2 Weeks | Admin and Reporting Backend Complete | Week 1 | 22/12/2024 - 28/12/2024 | - Develop API for admin functions (user/product management) - Implement reporting features (sales reports, user activity logs) - Ensure role-based access control | - Design admin dashboard UI components (React/Angular) - Use data visualization libraries like Chart.js, D3.js | - Design admin dashboard UI for mobile - Ensure proper layout for small screens and responsive data visualizations
|  |  | Week 2 | 29/12/2024 - 04/01/2025 | - Integrate backend admin features with frontend - Perform unit and integration testing - Document API endpoints and usage | - Implement admin dashboard and reporting UI - Test reporting features for web | - Implement mobile admin dashboard UI - Test for mobile usability and ensure clear data presentation
9. Sprint 7: Final Testing and Refinements | 2 Weeks | Final Testing Complete | Week 1 | 05/01/2025 - 11/01/2025 | - Conduct comprehensive testing (functional, integration, performance) - Fix any bugs/issues based on priority | - Finalize and polish all UI components based on testing feedback (web) | - Finalize and polish mobile UI components based on testing feedback
|  |  | Week 2 | 12/01/2025 - 18/01/2025 | - Perform final round of testing and QA - Prepare deployment documentation and user manuals | - Ensure web UI is optimized for performance and cross-browser compatibility | - Ensure mobile UI is optimized for performance and cross-device compatibility
10. Deployment and Post-Deployment Support | 1 Week | Go-Live | Week 1 | 19/01/2025 - 25/01/2025 | - Deploy backend services to production environment - Monitor deployment and perform post-deployment testing - Provide post-deployment support | - Deploy UI to production - Ensure web components are functioning post-deployment | - Deploy mobile app to stores (iOS/Android) - Monitor for critical issues
11. Post-Launch Review and Iteration | 1 Week | Post-Launch Review Complete | Week 1 | 26/01/2025 - 01/02/2025 | - Collect user feedback - Address critical issues and plan future ite

## Sheet5
Backlog: Agile Project Management
Epic 1: User Management
Sprint 1: Backend User Management (2 Weeks)
User Story | Description | Acceptance Criteria | Priority | Estimated Effort | Dependencies | Status
US 1: User Registration API (Backend) | As a new user, I want to register for the platform by providing my email, password, and profile details so that I can create an account. | 1. API accepts email, password, and profile info. 2. Validation on email and password. 3. JWT token generated on success. 4. Errors handled for invalid input. | High | 5 Story Points | Database Design | To Do
US 2: Login API (Backend) | As a registered user, I want to log in so that I can securely access my account. | 1. API supports login with email and password. 2. JWT token generated on success. 3. Errors handled for invalid login. | High | 5 Story Points | User Registration API | To Do
US 3: User Profile UI (Web) | As a logged-in user, I want to view and edit my profile information on the web. | 1. UI displays profile info. 2. Form validation on inputs. 3. Changes updated via API. | Medium | 3 Story Points | User Registration API | To Do
US 4: User Profile UI (Mobile) | As a mobile user, I want to view and edit my profile on my mobile app. | 1. Mobile UI displays profile info. 2. Layout adapts to screen size. 3. Profile updates via API. | Medium | 3 Story Points | User Registration API, Mobile Design | To Do
Epic 2: Product Management
Sprint 2: Backend Product Management (2 Weeks)
User Story | Description | Acceptance Criteria | Priority | Estimated Effort | Dependencies | Status
US 1: Product Catalog API (Backend) | As a user, I want to browse the product catalog so that I can view available products. | 1. API returns product list. 2. Supports filtering and sorting. 3. Handles pagination. | High | 5 Story Points | Database Design | To Do
US 2: Product Listing UI (Web) | As a web user, I want to browse and filter products online. | 1. UI displays products. 2. Supports filtering and sorting. 3. Responsive design. | High | 3 Story Points | Product Catalog API | To Do
US 3: Product Listing UI (Mobile) | As a mobile user, I want to view the product catalog on my phone. | 1. Mobile UI displays product list. 2. Supports filtering. 3. Adapts to screen sizes. | High | 3 Story Points | Product Catalog API | To Do
Epic 3: Shopping Cart
Sprint 3: Backend Shopping Cart (2 Weeks)
User Story | Description | Acceptance Criteria | Priority | Estimated Effort | Dependencies | Status
US 1: Add to Cart API (Backend) | As a user, I want to add items to my shopping cart so that I can purchase them later. | 1. API adds product to cart. 2. Cart persists across sessions. 3. Total price auto-calculated. 4. Errors handled for invalid inputs. | High | 5 Story Points | Product Catalog API | To Do
US 2: Shopping Cart UI (Web) | As a web user, I want to view and update my cart to proceed to checkout. | 1. UI displays cart items. 2. Users can update quantities. 3. Total price updates in real-time. | Medium | 4 Story Points | Add to Cart API | To Do
US 3: Shopping Cart UI (Mobile) | As a mobile user, I want to view my shopping cart on the go. | 1. Mobile UI shows cart items. 2. Users can add/remove items. 3. Adapts to mobile screens. | Medium | 4 Story Points | Add to Cart API | To Do
Epic 4: Payment Integration
Sprint 5: Backend Payment Integration (2 Weeks)
User Story | Description | Acceptance Criteria | Priority | Estimated Effort | Dependencies | Status
US 1: Payment Processing API (Backend) | As a user, I want to pay for my order securely so that my transaction is completed. | 1. API integrates with payment gateway. 2. Payment status returned. 3. Follows PCI compliance. 4. Errors handled for failed payments. | High | 5 Story Points | Order Management | To Do
US 2: Payment UI (Web) | As a web user, I want to securely enter my payment details to complete my purchase. | 1. UI collects payment info. 2. Data sent securely to backend. 3. Users receive payment confirmation. | High | 3 Story Points | Payment Processing API | To Do
US 3: Payment UI (Mobile) | As a mobile user, I want to complete payments securely on my mobile. | 1. Mobile UI collects payment info. 2. Data sent securely to backend. 3. Payment status shown to user. | High | 3 Story Points | Payment Processing API | To Do
Epic 5: Final Testing and Refinement
Sprint 7: Final Testing and Refinements (2 Weeks)
User Story | Description | Acceptance Criteria | Priority | Estimated Effort | Dependencies | Status
US 1: Comprehensive Testing | As a developer, I want to ensure the system functions as expected so that users have a seamless experience. | 1. Functional testing for all components. 2. Integration testing for backend/frontend. 3. Load testing for performance. 4. Security testing. | High | 10 Story Points | All Development Complete | To Do
Epic 6: Post-Launch Support
Sprint 10: Deployment and Post-Deployment Support (1 Week)
User Story | Description | Acceptance Criteria | Priority | Estimated Effort | Dependencies | Status
US 1: Post-Deployment Testing | As a team, I want to ensure that the deployment to production goes smoothly so that there are no issues. | 1. Post-deployment testing on production environment. 2. Ensure no critical issues. 3. Monitor system performance. 4. Set up support channels. | High | 4 Story Points | Production Deployment | To Do